## Plan
Name : | Bug Tracker
[6 empty] | November | [7 empty] | December | [30 empty] | Jan
Tasks | Status | Planned |  | Actual |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
|  | Start Date | End Date | Start Date | End Date | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
Setup | Complete | 2020-11-23 | 2020-11-23 | 2020-11-23 | 2020-11-23
1. Installations | Complete | 2020-11-23 | 2020-11-23 | 2020-11-23 | 2020-11-23 | bar: November Mon
User |  | 2020-11-24 | 2020-12-11
1. form : create ticket |  | 2020-11-24 | 2020-11-24 | 2020-11-24 | 2020-11-24 | bar: November Tue
2. view : list of tickets |  | 2020-11-25 | 2020-11-27 | 2020-11-25 | 2020-11-28 | bar: November Wed to November Fri
3. view : ticket details |  | 2020-12-09 | 2020-12-10 | bar: December Wed to December Thu
4. func : notifications |  | 2020-12-11 | 2020-12-11 | bar: December Fri
Login |  | 2020-11-27 | 2020-11-27 | 2020-11-27 | 2020-11-27
view : login page setup |  | 2020-11-27 | 2020-11-27 | 2020-11-27 | 2020-11-27 | bar: November Fri
Developer |  | 2020-11-30 | 2020-12-12
1. form : create ticket |  | 2020-11-30 | 2020-11-30 | bar: November Mon
2. view : list of tickets |  | 2020-11-30 | 2020-11-30 | bar: November Mon
3. view : ticket details |  | 2020-12-01 | 2020-12-03 | bar: December Tue to December Thu
4. view : list of projects |  | 2020-12-04 | 2020-12-05 | bar: December Fri to December Sat
5. view : project details |  | 2020-12-06 | 2020-12-08 | bar: December Sun to December Tue
6. func : notifications |  | 2020-12-11 | 2020-12-12 | bar: December Fri to December Sat
Administrator |  | 2020-12-18 | 2020-12-23
1. view : landing page |  | 2020-12-18 | 2020-12-18 | bar: December Fri
2. view : list of users |  | 2020-12-18 | 2020-12-18 | bar: December Fri
3. func : add users |  | 2020-12-19 | 2020-12-19 | bar: December Sat
4. func : manage users |  | 2020-12-19 | 2020-12-19 | bar: December Sat
5. view : list of projects |  | 2020-12-20 | 2020-12-20 | bar: December Sun
6. view : project details |  | 2020-12-20 | 2020-12-20 | bar: December Sun
7. func : manage projects |  | 2020-12-21 | 2020-12-21 | bar: December Mon
8. func : manage project users |  | 2020-12-22 | 2020-12-22 | bar: December Tue
9. view : list of tickets |  | 2020-12-22 | 2020-12-22 | bar: December Tue
10. view : ticket details |  | 2020-12-22 | 2020-12-22 | bar: December Tue
11. func : Manage tickets |  | 2020-12-23 | 2020-12-23 | bar: December Wed
Project Manager |  | 2020-12-24 | 2020-12-28
1. view : landing page |  | 2020-12-24 | 2020-12-26 | bar: December Thu to December Sat
2. view : list of projects |  | 2020-12-27 | 2020-12-27 | bar: December Sun
3. view : project details |  | 2020-12-27 | 2020-12-27 | bar: December Sun
4. view : list of tickets |  | 2020-12-28 | 2020-12-28 | bar: December Mon
5. view : ticket details |  | 2020-12-28 | 2020-12-28 | bar: December Mon
Authorizations & Testing |  | 2020-12-29 | 2020-12-30
Deploy |  | 2020-01-01 | 2020-01-02